Items of Interest – Elections Officials

Updated February 16, 2010

| Item | Contact | Status |
| --- | --- | --- |
| Post Election Audit Bill | SOS: Jennie Bretschneider # Phone: (916) 651-8297 County PEMT Working Group: Dean Logan Janice Atkinson Darlene Bonds Cathy Darling Elaine Larson Elaine Ginnold Joe Holland Lisa Thomas Jim McCauley Matt Morales Gail Pellerin Philip Chantri Ryan Ronco Deborah Seiler Tricia Webber | SOS is considering sponsoring a bill that would create a pilot program to test new risk-limiting audits, which Santa Cruz, Yolo, and Marin informally tested with election auditing experts in 2008 and 2009. |
| Poll Worker Training Standards | # SOS: Jana Lean # Phone: (916) 653-5144 & # Robbie Anderson # Phone: (916) 653-1690 County Working Group: Dave MacDanold Cathy Hernandez Ken Baird Tim McNamara Dean Logan Neal Kelley Nicole Alejandre Carrie Pickmosa Elaine Larson Tricia Webber Lindsey McWilliams Janice Atkinson Gloria Colter | Draft standards were sent to all counties for comments on January 8, 2010. SOS staff is currently reviewing comments received and we anticipate that the final version of standards will be released by the end of February. |
| Item | Contact | Status |
| Accessibility Guidelines & Survey | SOS: Debbie O’Donoghue Phone: (916) 653-6173 County VAAC members: Gail Pellerin Tim McNamara Elaine Ginnold | SOS contracted with Dept. of Rehab to update guidelines and survey tool and provide a county elections official training program. A reminder that these are guidelines to help county elections officials comply with existing laws. They do not make new law or add requirements that do not currently exist under the law. Survey tool is an instrument designed to help local elections officials comply with the law. Elections officials are not required to utilize the tool. Vetted draft guidelines and survey tool with county elections officials and statewide VAAC in fall 2009. SOS in the final review phase and will post guidelines and survey tool on the website soon. Five regional training sessions will be held in March. Mock training scheduled for February 17. |
| HAVA State Plan | # SOS: Chris Reynolds Phone: 651-7837 County members: Rebecca Martinez Dean Logan Neal Kelley | Five meetings held; comments received; DRAFT State Plan Update being revised based on input received. Revisions to be reviewed by Secretary of State and refined at future meeting TBA, if necessary. Following completion of the DRAFT State Plan Update, the updated plan will be made available for public comment. The comment period will be noticed and interested parties, including county elections officials, will be notified. |
| HAVA Accessibility Grant Program | SOS: Debbie O’Donoghue Phone: (916) 653-6173 | The Vote Grant Program II applications were due from county elections officials on Aug. 24, 2009. SOS review began Sept. 1, 2009 Grants were awarded on November 3, 2009. Secretary of State looking at creating a third round of funding. |
| Item | Contact | Status |
| Conditional Voter Registration (CVR) Program | SOS: Jennie Bretschneider Phone: (916) 651-8297 Working Group: Janice Atkinson Joe Holland Gail Pellerin Elaine Ginnold Neal Kelley Freddie Oakley Dean Logan | CACEO Board of Directors voted to support CVR in concept Aug. 20, 2009. SOS does not plan to sponsor a CVR bill in 2010 but may do so in 2011. AB 1531 (Portantino) creating a different Election Day Registration program was introduced in 2009 but did not move. The SOS did not sponsor or support AB 1531. In January 2010, Senator Leland Yee announced plans to introduce a different Election Day Registration bill. The SOS is not involved with Senator Yee’s bill. |
| VoteCal | SOS: Fred Wood Phone: (916) 653-3785 & Mary Winkley Phone: (916) 653-8365 Jill LaVine, Sacramento (Chair) Dean Logan, Los Angeles Janice Atkinson, Sonoma Deborah Seiler, San Diego Gail Pellerin, Santa Cruz Bev Ross, Tehama Terry Hansen, Yuba | This committee’s mission is to make decisions on questions that arise as to business processes. Their first order of business will be to establish a uniform practice as to the date entered when a voter registration card is entered into the system. The committee will be responsive to other issues as they arise during the life of the VoteCal Project and especially over the next few months during the Design Phase. |
| Item | Contact | Status |
| VoteCal Discovery Sessions | SOS: Fred Wood Phone: (916) 653-3785 & Mary Winkley Phone: (916) 653-8365 DFM Counties Candy Lopez, Contra Costa Juan Witrago, Fresno, Melvin Briones, Marin Tony Aquilino, Marin Justin Berardino, Orange Doug Kinzle, Riverside Roberta Kanelos, Sacramento Joe Le, Santa Clara ES&S Counties Michele Wales, Alameda Ray Ching, Los Angeles Michael Petrucello, Los Angeles Charlie Wallis, San Diego Lindsey McWilliams, Solano Aaron Rosa, Stanislaus Votec County No Votec County representation, however John Medcalf, Votec’s President is present at the Discovery Sessions. EMS Vendors All three remaining Election Management System Vendors (DFM, ES&S, and Votec) which collectively represent all 58 counties are also present and represented at the Discovery Sessions. | Representatives from a cross-section of California counties have been assigned to work with Catalyst Consulting Group, the VoteCal vendor. They will participate in “Discovery Sessions” wherein Catalyst will present an overview of the VoteCal System’s proposed functionality, features, and requirements and clarify through county input and feedback on how county elections officials and their staff would like to see VoteCal work. There are five three-day Discovery Sessions being conducted over the period from February 9, 2010 through March 11, 2010. |
| Item | Contact | Status |
| Future of Voting Systems Public Hearing | SOS: Jennie Bretschneider Phone: (916) 651-8297 Gail Pellerin, Santa Cruz Cathy Darling, Shasta Dean Logan, Los Angeles Jill LaVine, Sacramento Deborah Seiler, San Diego Tim McNamara, Los Angeles Rebecca Martinez, Madera | Hearing was held February 8, 2010. Hearing information, including written comments, video archive and transcript will be posted at www.sos.ca.gov/voting-systems/hearings/index.htm |
| May 19, 2009 Special Election Reimbursement | Contacts: Steve Weir, Contra Costa Janice Atkinson, Sonoma | The Governor inserted $68.2 million to reimburse counties for the May 19, 2009 statewide special election. Counties would not see any funds until 30 to 60 days after the budget is adopted and signed. |